## Team
Smart Restaurant Management System — Team Information
Name Surname | Student ID | Role | Main Responsibilities
Batuhan İnan | B2280.060082 | Backend Developer | API design, Authentication (JWT), Role-based access, Order logic, Swagger/OpenAPI, Error handling
Emir İnanç Şeker | B2380.060019 | Frontend Developer | UI/UX, Dashboard, API integration, Documentation management (README/docs), Excel planning (timeline & budget), GitHub organization
İzzet Ali Arslan | B2280.060035 | Database & Analytics Developer | ERD & normalization (1NF–3NF), migrations, indexes, relations/constraints, reporting queries (SQL aggregation), views/stored procedures (optional), performance tuning

## Timeline (14 Weeks)
Weekly Timeline (Aligned with Course Weekly Assignments)
Week | Course Focus / Deliverable | Planned Work (Project) | Owner | Evidence (GitHub/Jira)
1 | Team formation + Project idea (1-page summary) | Create repo structure, create Jira project + epics/stories, draft proposal | Frontend (Member 2) | README + proposal draft + Jira board
2 | SDLC phases + simple project timeline | Confirm SDLC (Scrum), finalize sprint plan (7 sprints / 2-week) | Backend (Member 1) | SDLC section in README/docs
3 | Functional & non-functional requirements | Write requirements (FR/NFR), user stories backlog | All | docs/Requirements.md
4 | WBS diagram | Create WBS (deliverables/tasks) mapped to epics/stories | Frontend (Member 2) | docs/WBS.png or .md
5 | Gantt chart | Create Gantt in Excel (durations, dependencies) | Frontend (Member 2) | docs/Gantt.xlsx or .png
6 | RACI matrix | Create RACI table for roles & responsibilities | Frontend (Member 2) | docs/RACI.xlsx or .md
7 | Midterm / progress review (%50) | MVP skeleton: auth + products + db schema + basic UI | All | Jira progress + demo notes
8 | Risk register | Risk register (probability/impact/mitigation) | Frontend (Member 2) | docs/Risk_Register.xlsx
9 | Quality assurance + test plan | Test plan (unit/integration/UAT) + quality metrics | Backend (Member 1) | docs/Test_Plan.md
10 | Cost estimation + budgeting | Finalize budget & assumptions | Frontend (Member 2) | docs/Budget.xlsx
11 | Agile: backlog + sprint plan | Refine backlog, plan next sprint in Jira | Backend (Member 1) | Jira backlog + sprint plan
12 | Monitoring & control + status report | Status report (KPIs, variance), burndown screenshot | Frontend (Member 2) | docs/Status_Report.md
13 | Final presentation + demo | Slides + demo checklist | Frontend (Member 2) | docs/Slides.pdf + demo video/link
14 | Final report + reflection | Final report + retrospective | Frontend (Member 2) | docs/Final_Report.pdf

## Budget
Budget Planning (Resources • Time • Members)
Category | Resource | Who | Estimated Hours | Unit Cost (TRY) | Total (TRY)
People (Academic) | Backend Development | Member 1 | 60 | 0 | 0
People (Academic) | Frontend Development | Member 2 | 60 | 0 | 0
People (Academic) | Database & Analytics | Member 3 | 60 | 0 | 0
Tools/Hosting | Domain (optional) | Team | - | 300 | 300
Tools/Hosting | Database hosting (if separate) | Team | - | 0 | 0
Misc | QR code generator | Team | - | 0 | 0
TOTAL |  |  |  |  | 300